## Purchase summary
MP Adams Plot 3, Eckington - Procurement C01
Client MP Adams. All quantities include waste per P-06; each purchase split by section below.
Group | Purchase item | Unit | Order qty | Sections
Timber | 25x100 (4x1) green/brown treated rough-sawn @ 5.4m | lengths | 23 | GF temporary bracing: 10; FF temporary bracing: 9; Gable temporary bracing: 4
Timber | 38x140 C16 @ 4.8m | lengths | 335 | GF sole plates: 12; GF head binder: 12; FF head binder: 11; GF panels: 134; FF panels: 130; Gable panels: 36
Timber | 38x89 C16 @ 4.8m | lengths | 116 | GF sole plates: 3; GF temporary bracing: 4; FF temporary bracing: 4; Gable temporary bracing: 2; GF window battens: 7; FF window battens: 6; Gable window battens: 1; GF panels: 20; FF panels: 69
Timber | 45x145 C24 @ 4.8m | lengths | 24 | GF panels: 12; FF panels: 10; Gable panels: 2
Timber | 45x195 C24 @ 4.8m | lengths | 14 | First floor edgebinder: 10; First floor edgebinder rips: 4
Engineered beams | Glulam 100x240 GL24h @ 1632mm | no. | 2 | First floor beams: 2
Engineered beams | Glulam 100x240 GL24h @ 2690mm | no. | 1 | First floor beams: 1
Engineered beams | Glulam 100x240 GL24h @ 3166mm | no. | 2 | First floor beams: 2
Steel (TLS supply) | UB254x102x28 S355 @ 5657mm | no. | 1 | First floor steel: 1
Steel (TLS supply) | UB254x146x43 S355 @ 5620mm | no. | 1 | Roof-level steel (on FF walls): 1
Sheet materials | Egger P5 22mm flooring 600x2400 | sheets | 61 | First floor deck: 61
Sheet materials | Marine ply 14mm 1220x2440 | sheets | 1 | First floor beams: 1
Sheet materials | OSB/3 9mm 1197x2397 | sheets | 91 | First floor waist band: 5; GF panels: 38; FF panels: 34; Gable panels: 14
Sheet materials | Plywood 9mm 1220x2440 (panel end caps) | sheets | 2 | GF panels: 1; FF panels: 1
Insulation | PIR 120mm 1200x2400 | boards | 55 | GF panels: 21; FF panels: 23; Gable panels: 11
Membranes | Breather membrane 100m x 2.7m roll | rolls | 1 | GF panels: 0.3; FF panels: 0.33; Gable panels: 0.17; First floor waist band: 0.08
Membranes | DPC 300mm x 30m roll | rolls | 1 | GF sole plates: 1
Membranes | DPC 600mm x 30m roll | rolls | 2 | GF sole plates: 2
Metalwork | Simpson Strong-Tie ETFSS timber frame holding-down strap | no. | 13 | GF holding-down: 13
Fixings | 50mm staples (box of 5,000) | boxes | 2 | GF panels: 0.65; FF panels: 0.54; Gable panels: 0.25
Fixings | 90mm ring-shank nails (box of 2,500) | boxes | 4 | GF panels: 1.32; FF panels: 1.75; Gable panels: 0.26
Fixings | Brick ties (box of 250) | boxes | 4 | External walls GF + FF + gables: 3.17
Fixings | M7.5x100 concrete screw (box of 100) | boxes | 2 | GF sole plates: 1.25; GF temporary bracing: 0.4
Sealants & adhesives | D4 adhesive 1L | bottles | 10 | First floor deck: 9.38
Sealants & adhesives | Silicone sealant 280ml | tubes | 7 | GF sole plates: 6.72

## By section
Group | Purchase item | Unit | Section | Net qty | Order qty (with waste) | Basis | Drawing | Note
Timber | 25x100 (4x1) green/brown treated rough-sawn @ 5.4m | lengths | GF temporary bracing | 9 | 10 | 18 x 2.7m braces, 2 per 5.4m, +5% | P3-GA-01
Timber | 25x100 (4x1) green/brown treated rough-sawn @ 5.4m | lengths | FF temporary bracing | 8 | 9 | 15 x 2.7m braces, 2 per 5.4m, +5% | P3-GA-02
Timber | 25x100 (4x1) green/brown treated rough-sawn @ 5.4m | lengths | Gable temporary bracing | 3 | 4 | 6 x 2.7m braces, 2 per 5.4m, +5% | P3-GA-03
| TOTAL 25x100 (4x1) green/brown treated rough-sawn @ 5.4m | lengths |  |  | 23
Timber | 38x140 C16 @ 4.8m | lengths | GF sole plates | 11 | 12 | 17 pcs / 51.8m -> 11 x 4.8m cut-optimised (3mm kerf) +5% | P3-SP-01
Timber | 38x140 C16 @ 4.8m | lengths | GF head binder | 11 | 12 | 18 pcs / 51.7m -> 11 x 4.8m cut-optimised (3mm kerf) +5% | P3-GA-01
Timber | 38x140 C16 @ 4.8m | lengths | FF head binder | 10 | 11 | 15 pcs / 43.6m -> 10 x 4.8m cut-optimised (3mm kerf) +5% | P3-GA-02
Timber | 38x140 C16 @ 4.8m | lengths | GF panels | 127 | 134 | 364 pcs / 592.8m -> 127 x 4.8m cut-optimised (3mm kerf) +5%; 1 ripped to 38x109; 1 ripped to 10x140 | Manufacture GF
Timber | 38x140 C16 @ 4.8m | lengths | FF panels | 123 | 130 | 354 pcs / 565.2m -> 123 x 4.8m cut-optimised (3mm kerf) +5%; 1 ripped to 10x140; 25 ripped to 38x117 | Manufacture FF
Timber | 38x140 C16 @ 4.8m | lengths | Gable panels | 34 | 36 | 107 pcs / 157.3m -> 34 x 4.8m cut-optimised (3mm kerf) +5% | Manufacture Gable
| TOTAL 38x140 C16 @ 4.8m | lengths |  |  | 335
Timber | 38x89 C16 @ 4.8m | lengths | GF sole plates | 2 | 3 | 4 pcs / 6.9m -> 2 x 4.8m cut-optimised (3mm kerf) +5% | P3-SP-01
Timber | 38x89 C16 @ 4.8m | lengths | GF temporary bracing | 3 | 4 | 18 pcs / 10.8m -> 3 x 4.8m cut-optimised (3mm kerf) +5%; 600 bracing noggins | P3-GA-01
Timber | 38x89 C16 @ 4.8m | lengths | FF temporary bracing | 3 | 4 | 15 pcs / 9.0m -> 3 x 4.8m cut-optimised (3mm kerf) +5%; 600 bracing noggins | P3-GA-02
Timber | 38x89 C16 @ 4.8m | lengths | Gable temporary bracing | 1 | 2 | 6 pcs / 3.6m -> 1 x 4.8m cut-optimised (3mm kerf) +5%; 600 bracing noggins | P3-GA-03
Timber | 38x89 C16 @ 4.8m | lengths | GF window battens | 6.5 | 7 | 41 battens / 55.0m of 38x43 -> 14 x 4.8m 38x43 (+5%), ripped 2 per 38x89 | P3-GA-01
Timber | 38x89 C16 @ 4.8m | lengths | FF window battens | 5 | 6 | 36 battens / 42.8m of 38x43 -> 11 x 4.8m 38x43 (+5%), ripped 2 per 38x89 | P3-GA-02
Timber | 38x89 C16 @ 4.8m | lengths | Gable window battens | 0.5 | 1 | 4 battens / 3.9m of 38x43 -> 2 x 4.8m 38x43 (+5%), ripped 2 per 38x89 | P3-GA-03
Timber | 38x89 C16 @ 4.8m | lengths | GF panels | 19 | 20 | 64 pcs / 87.4m -> 19 x 4.8m cut-optimised (3mm kerf) +5%; 1 ripped to 38x34 | Manufacture GF
Timber | 38x89 C16 @ 4.8m | lengths | FF panels | 65 | 69 | 225 pcs / 303.2m -> 65 x 4.8m cut-optimised (3mm kerf) +5% | Manufacture FF
| TOTAL 38x89 C16 @ 4.8m | lengths |  |  | 116
Timber | 45x145 C24 @ 4.8m | lengths | GF panels | 11 | 12 | 43 pcs / 49.0m -> 11 x 4.8m cut-optimised (3mm kerf) +5%; 2 ripped to 41x145 | Manufacture GF
Timber | 45x145 C24 @ 4.8m | lengths | FF panels | 9 | 10 | 38 pcs / 40.3m -> 9 x 4.8m cut-optimised (3mm kerf) +5%; 4 ripped to 41x145 | Manufacture FF
Timber | 45x145 C24 @ 4.8m | lengths | Gable panels | 1 | 2 | 3 pcs / 2.5m -> 1 x 4.8m cut-optimised (3mm kerf) +5% | Manufacture Gable
| TOTAL 45x145 C24 @ 4.8m | lengths |  |  | 24
Timber | 45x195 C24 @ 4.8m | lengths | First floor edgebinder | 9 | 10 | 16 edgebinders / 39.4m cut-optimised +5% | P3-FL-01
Timber | 45x195 C24 @ 4.8m | lengths | First floor edgebinder rips | 3.33 | 4 | 45x59 rips 10 x 4.8m (+5%), 3 per 45x195 | P3-FL-01
| TOTAL 45x195 C24 @ 4.8m | lengths |  |  | 14
Engineered beams | Glulam 100x240 GL24h @ 1632mm | no. | First floor beams | 2 | 2 | GL3; GL5 | P3-FL-01 | Cut to length
| TOTAL Glulam 100x240 GL24h @ 1632mm | no. |  |  | 2
Engineered beams | Glulam 100x240 GL24h @ 2690mm | no. | First floor beams | 1 | 1 | GL4 | P3-FL-01 | Cut to length
| TOTAL Glulam 100x240 GL24h @ 2690mm | no. |  |  | 1
Engineered beams | Glulam 100x240 GL24h @ 3166mm | no. | First floor beams | 2 | 2 | GL1; GL2 | P3-FL-01 | Cut to length
| TOTAL Glulam 100x240 GL24h @ 3166mm | no. |  |  | 2
Steel (TLS supply) | UB254x102x28 S355 @ 5657mm | no. | First floor steel | 1 | 1 | P-22 TLS supply | P3-FL-01
| TOTAL UB254x102x28 S355 @ 5657mm | no. |  |  | 1
Steel (TLS supply) | UB254x146x43 S355 @ 5620mm | no. | Roof-level steel (on FF walls) | 1 | 1 | P-22 TLS supply | P3-GA-02 / P3-RF-01
| TOTAL UB254x146x43 S355 @ 5620mm | no. |  |  | 1
Sheet materials | Egger P5 22mm flooring 600x2400 | sheets | First floor deck | 56.1 | 61 | 80.8 m2 laid, +7.5% | P3-FL-01
| TOTAL Egger P5 22mm flooring 600x2400 | sheets |  |  | 61
Sheet materials | Marine ply 14mm 1220x2440 | sheets | First floor beams | 0.45 | 1 | 5 packers / 12.1m of 100 strip on top of 240 GL = 254 (D-25); 11 strips per sheet, +7.5% | P3-FL-01
| TOTAL Marine ply 14mm 1220x2440 | sheets |  |  | 1
Sheet materials | OSB/3 9mm 1197x2397 | sheets | First floor waist band | 4.25 | 5 | 17 x 290 strips, 4 per sheet, +7.5% | P3-FL-01
Sheet materials | OSB/3 9mm 1197x2397 | sheets | GF panels | 38 | 38 | 79 pieces / 100.8 m2 nested on 38 sheets (P3-CP-OSB, 2mm kerf); exact waste 8.2 m2 incl. 3 reusable offcuts; no % allowance (D-28) | Manufacture GF / P3-CP-OSB
Sheet materials | OSB/3 9mm 1197x2397 | sheets | FF panels | 34 | 34 | 67 pieces / 88.1 m2 nested on 34 sheets (P3-CP-OSB, 2mm kerf); exact waste 9.4 m2 incl. 2 reusable offcuts; no % allowance (D-28) | Manufacture FF / P3-CP-OSB
Sheet materials | OSB/3 9mm 1197x2397 | sheets | Gable panels | 14 | 14 | 34 pieces / 33.8 m2 nested on 14 sheets (P3-CP-OSB, 2mm kerf); exact waste 6.4 m2 incl. 1 reusable offcuts; no % allowance (D-28) | Manufacture Gable / P3-CP-OSB
| TOTAL OSB/3 9mm 1197x2397 | sheets |  |  | 91
Sheet materials | Plywood 9mm 1220x2440 (panel end caps) | sheets | GF panels | 0.7 | 1 | 6 end cap strips / 2.1 m2, +7.5% | Manufacture GF
Sheet materials | Plywood 9mm 1220x2440 (panel end caps) | sheets | FF panels | 0.69 | 1 | 6 end cap strips / 2.0 m2, +7.5% | Manufacture FF
| TOTAL Plywood 9mm 1220x2440 (panel end caps) | sheets |  |  | 2
Insulation | PIR 120mm 1200x2400 | boards | GF panels | 21 | 21 | 154 pieces / 54.9 m2 nested on 21 boards (P3-CP-PIR, 2mm kerf); exact waste 5.5 m2; no % allowance (D-28); external walls only (P-11) | Manufacture GF / P3-CP-PIR
Insulation | PIR 120mm 1200x2400 | boards | FF panels | 23 | 23 | 164 pieces / 60.0 m2 nested on 23 boards (P3-CP-PIR, 2mm kerf); exact waste 6.2 m2; no % allowance (D-28); external walls only (P-11) | Manufacture FF / P3-CP-PIR
Insulation | PIR 120mm 1200x2400 | boards | Gable panels | 11 | 11 | 63 pieces / 27.8 m2 nested on 11 boards (P3-CP-PIR, 2mm kerf); exact waste 3.9 m2; no % allowance (D-28); external walls only (P-11) | Manufacture Gable / P3-CP-PIR
| TOTAL PIR 120mm 1200x2400 | boards |  |  | 55
Membranes | Breather membrane 100m x 2.7m roll | rolls | GF panels | 0.29 | 0.3 | 74.0 m2 external panel face, 150 laps, +5% | Manufacture GF
Membranes | Breather membrane 100m x 2.7m roll | rolls | FF panels | 0.31 | 0.33 | 79.2 m2 external panel face, 150 laps, +5% | Manufacture FF
Membranes | Breather membrane 100m x 2.7m roll | rolls | Gable panels | 0.16 | 0.17 | 41.7 m2 external panel face, 150 laps, +5% | Manufacture Gable
Membranes | Breather membrane 100m x 2.7m roll | rolls | First floor waist band | 0.07 | 0.08 | 17 x 450 strips (222 per roll) | P3-FL-01
| TOTAL Breather membrane 100m x 2.7m roll | rolls |  |  | 1
Membranes | DPC 300mm x 30m roll | rolls | GF sole plates | 0.76 | 1 | 19.8m + 10 laps x 300 = 22.8m, +5% | P3-SP-01
| TOTAL DPC 300mm x 30m roll | rolls |  |  | 1
Membranes | DPC 600mm x 30m roll | rolls | GF sole plates | 1.46 | 2 | 39.0m + 8 laps x 600 = 43.8m, +5% | P3-SP-01
| TOTAL DPC 600mm x 30m roll | rolls |  |  | 2
Metalwork | Simpson Strong-Tie ETFSS timber frame holding-down strap | no. | GF holding-down | 13 | 13 | 13 positions, engineer 26-431-S-0001 Detail 1 | P3-GA-01 | Fixings to Simpson guidance
| TOTAL Simpson Strong-Tie ETFSS timber frame holding-down strap | no. |  |  | 13
Fixings | 50mm staples (box of 5,000) | boxes | GF panels | 2952 | 0.65 | 2952 staples (@150 edges / 300 field) +10% | Manufacture GF
Fixings | 50mm staples (box of 5,000) | boxes | FF panels | 2474 | 0.54 | 2474 staples (@150 edges / 300 field) +10% | Manufacture FF
Fixings | 50mm staples (box of 5,000) | boxes | Gable panels | 1127 | 0.25 | 1127 staples (@150 edges / 300 field) +10% | Manufacture Gable
| TOTAL 50mm staples (box of 5,000) | boxes |  |  | 2
Fixings | 90mm ring-shank nails (box of 2,500) | boxes | GF panels | 3010 | 1.32 | 3010 nails (joints x3, multi-ply @150) +10% | Manufacture GF
Fixings | 90mm ring-shank nails (box of 2,500) | boxes | FF panels | 3976 | 1.75 | 3976 nails (joints x3, multi-ply @150) +10% | Manufacture FF
Fixings | 90mm ring-shank nails (box of 2,500) | boxes | Gable panels | 588 | 0.26 | 588 nails (joints x3, multi-ply @150) +10% | Manufacture Gable
| TOTAL 90mm ring-shank nails (box of 2,500) | boxes |  |  | 4
Fixings | Brick ties (box of 250) | boxes | External walls GF + FF + gables | 721 | 3.17 | 194.9 m2 net external wall x 3.7/m2 +10% | P-21
| TOTAL Brick ties (box of 250) | boxes |  |  | 4
Fixings | M7.5x100 concrete screw (box of 100) | boxes | GF sole plates | 114 | 1.25 | 114 screws +10% | P3-SP-01
Fixings | M7.5x100 concrete screw (box of 100) | boxes | GF temporary bracing | 36 | 0.4 | 36 screws (2 per noggin) +10% | P3-GA-01
| TOTAL M7.5x100 concrete screw (box of 100) | boxes |  |  | 2
Sealants & adhesives | D4 adhesive 1L | bottles | First floor deck | 9.38 | 9.38 | 1L per 6.5 sheets | P3-FL-01
| TOTAL D4 adhesive 1L | bottles |  |  | 10
Sealants & adhesives | Silicone sealant 280ml | tubes | GF sole plates | 6.11 | 6.72 | 114 holes x 15ml = 1.71L +10% | P3-SP-01
| TOTAL Silicone sealant 280ml | tubes |  |  | 7

## Rules
P-06 | Linear timber cut-optimised into 4.8m stock (3mm kerf) then +5%; sheets +7.5%; PIR +10%; fixings, silicone, glue +10% rounded up to purchase units; DPC and membrane laps + 5%, rounded up to rolls.
D-28 | Panel OSB and PIR are ordered at the exact nested sheet count from the cutting packs (2mm kerf, D-27): the waste is known, so no percentage is added.
P-07 | All timber in 4.8m lengths; anything over 4.8m flagged as a special.
P-08 | Edgebinder 45x195 C24 @ 4.8m; 45x59 rips 3 per 45x195 (3mm kerf).
P-09 | Waist band ripped from 1197x2397 9mm OSB/3, 4 x 290 strips per sheet.
P-10 | Breather 100m x 2.7m rolls; 450 strips cut off the roll (~222 per roll); one line with panel breather.
P-11 | Nails 3 x 90 ring-shank per joint / noggin end, multi-ply @150 staggered (both sides > 2 ply, 3 lots > 3 ply), boxes 2,500. Staples 50mm @150 edges / 300 field, boxes 5,000. No VCL, no mineral wool. PIR 120 to external walls only.
P-15 | One 2.7m 4x1 brace per panel joint on EX / IL / gable panels; 600 38x89 noggin each.
P-16 | Window battens 38x43 from 38x89 C16 ripped in half, external openings only.
P-21 | Brick ties 3.7/m2 net external wall area (GF + FF + gables less openings) +10%, boxes of 250.
P-22 | Steel beams are TLS supply.
D-17 | Head binder on external and load-bearing walls only.
Acorn | Metal-web joists, hangers, strongbacks, noggins and roof trusses / cut roof by Acorn Timber Engineering - not in TLS procurement.